## Risk library
Sector | Sub-sector | Project type | Risk category | Risk description | Risk likelihood | Risk impact | Risk rating | Potential risk response (avoid, reduce, transfer, accept) | Fast-growing Cities | Smaller Cities and Regional Centres | Small Towns, Rural Communities and Remote Areas | Developing Regions and Northern Australia
Transport | Airports | Airport runways | Weather risk | If airports are located in coastal areas, then proposed runway sites will need to be flat and low in nature, and there will be a risk of inundation during flood events and future climate change impacts such as storm surge and sea level rise, leading to increased operations and maintenance costs and safety impacts. | Unlikely | Major | Medium | 1. Reduce - Ensure potential operational impacts are well understood in the start through stakeholder consultation. 2. Reduce - Develop a plan for future identification and management of climate change risks and impacts. 3. Accept - Consider appropriate risk allowances in the planning. | yes | yes | yes | yes
Transport | Airports | Airport runways | Stakeholder risk | If landowners, local residents and relevant stakeholders expectations of noise are not considered in planning and design, then there is a risk that these stakeholders will feel unheard or unconsulted, resulting in backlash at new/extension of airport runways and ultimately lead to reputational damage. | Likely | Insignificant | Low | 1. Reduce - Establish environmental control processes and procedures in place that are rolled out early in collaboration with the contractor. This should also include consideration to environmental controls required post operationalisation. Ensure this consideration has been taken on board in the stakeholder engagement plan and design considerations. 2. Reduce - Commission environmental studies throughout the course of the project to ensure the noise and vibration pollution can be controlled. | yes | yes | yes | yes
Transport | Airports | Airport runways | Design inadequacy risk | If low-level airspace is a factor or consideration in the design for the proposed airport runway, then there is a risk that the design could become overly complex, resulting in an increase in scope and cost overruns. | Unlikely | Major | Medium | 1. Reduce - Implement processes to identify projects considering low-airspace and potential mitigations. 2. Accept - Consider appropriate risk allowances for future design and planning. | yes | yes | yes | yes
Transport | Airports | Airport runways | Project management risk | If procurement negotiation with contractors is extended, then there is a risk that critical milestones are impacted, leading to schedule delays. | Possible | Minor | Medium | 1. Reduce - Ensure potential operational impacts are well understood in the start through stakeholder consultation. 2. Transfer - Negotiate a preferred model to transfer risk allocations to relevant proponents. 3. Accept - Consider appropriate risk allowances in the schedule and timeline estimates. | yes | yes | yes | yes
Transport | Airports | Airport runways | Benefits realisation risk | If there are extended outbreaks and COVID-19 restrictions, then there is a risk of reduced passenger numbers/customer demand, resulting in the unrealised project benefits. | Almost certain | Moderate | High | 1. Reduce - Have a stakeholder engagement plan to encourage a broader the passenger mix (e.g. tourism, business), the more sustainable the route will be, and the level of risk exposure for airlines is reduced. 2. Reduce - Ensure potential operational impacts are well understood in the start through stakeholder consultation. 3. Transfer - Negotiate a preferred model to transfer risk allocations to relevant proponents. 4. Accept - Consider appropriate risk allowances in the cost estimate. | yes | yes | yes | yes
Transport | Airports | Airport runways | Planning risk | If there are ineffective strategies related to land acquisition, then there is a risk that land acquisition activities do not meet due diligence or ethical standards, resulting in higher acquisition costs above the competitive market rate, and reducing the viability of the project through cost overruns. | Possible | Major | High | 1. Reduce - Develop a structured acquisition plan for acquiring land for the project. 2. Transfer - Negotiate a preferred acquisition model to transfer risk allocations to relevant proponents. 3. Accept - Consider appropriate risk allowances in the cost estimates. | yes | yes | yes | yes
Transport | Airports | Airport runways | Stakeholder risk | If there are no formalised stakeholder management plans, then there is a risk that key project stakeholders, including those within the community, local governments and suppliers are unclear on expectations, leading to reputational damage to the project, and schedule delays. | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies. | yes | yes | yes | yes
Transport | Airports | Airport runways | Compliance/regulatory risk | If there are unclear or out of date acceptance criteria across each aspect of project deliverables (including specific areas of construction such as concrete slabs and walls), there is a risk of disputes between contractors relating to defect remediation requirements, resulting in schedule delays and potential cost overruns. | Possible | Major | High | 1. Reduce - Ensure that the Owner has a clear Quality Management Plan which details specific acceptance criteria and sign off points. Ensure that these sign off points are from the Owner’s team (i.e. not one of the contractors). | yes | yes | yes | yes
Transport | Airports | Airport runways | Planning risk | If there is a poor understanding, documentation and management of integrations within the project, or of dependencies in other projects, there is a risk of misalignment between project design, delivery and outcomes and across work packages, leading to rework of project design, construction and schedule delays. | Possible | Major | High | 1. Reduce - Ensure project plans and designs are finalised for related or nearby projects prior to construction. | yes | yes | yes | yes
Transport | Airports | Airport runways | Liability risk | If there is unclear documentation relating to defect liability in specific contract structures (e.g. liability to resolve defects for a Construct-only contract, where root cause of defect may be design related), there is a risk of disputes between contractors, resulting in schedule delays and potential cost overruns if parties are unable to agree liability. | Possible | Major | High | 1. Reduce - As part of contractual arrangements, ensure there is appropriate due diligence clauses for various contractors to complete their own due diligence activities to ensure liabilities can be allocated. 2. Accept - Consider assigning project contingency funds to cover these scenarios (particularly given the frequency of these risks occurring). | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arena/sporting facility | Design inadequacy risk | If demand modelling for site facilities utilisation is inaccurate or there is poor communications to drive uptake, then there is a risk of that objectives within the business case are not achieved, resulting in operational and reputational impacts. | Possible | Moderate | Medium | 1. Reduce - Develop and agree a benefits realisation plan which defines relevant expectations set out by the business case. 2. Reduce - Establish a process to reassess patronage modelling and validate assumptions as the project progresses. This may also include completing sensitivity analysis over variations to the modelling to consider contingency planning. 3. Accept - Consider appropriate risk allowances in business case and benefits realisation plan based on the sensitivity analysis. | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arena/sporting facility | Stakeholder risk | If relevant government planning bodies and community groups are not consulted appropriately, then there is a risk planning, environmental and statutory approvals are not received for development or redevelopment as per the project schedule or that the approval conditions are received late, resulting in cost overruns and schedule delays. | Unlikely | Major | Medium | 1. Reduce - Integrate key deadlines for submitting and receiving approval in the project schedule. 2. Reduce - Develop a stakeholder management plan, which includes early engagement with relevant local/state planning bodies. 3. Transfer - Develop a matrix of all required approvals and consider allocating risk to relevant contractors to obtain approval. | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arena/sporting facility | Population/demographics risks | If there is a lack of future considerations for the sporting facility, including demand and population trends, then there may be a lack of flexibility or longevity in the facility, resulting in an inability to meet future technology and sporting needs and increasing operations and maintenance costs. | Possible | Extreme | High | 1. Reduce - Develop an adaptable and scalable project plan that considers future technology and sporting needs. 2. Reduce - Undertake detailed modelling in subsequent project stages to increase certainty on future requirements and needs. | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arena/sporting facility | Stakeholder risk | If there is an inconsistent approach to stakeholder communications and engagement, then there may be misalignment in the expectations of local communities, government and clubs resulting in stakeholder and reputational impacts, breakdown in relations and project schedule delays. | Possible | Moderate | Medium | 1. Reduce - Develop a structured stakeholder management plan and communications plan, which includes early engagement with relevant communities, government representatives and clubs. | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arts facility | Communication risk | If a multi-party consistent approach to stakeholder communications does not exist, then there may be misalignment in the communications published by different parties (e.g. communications published by the government, project team and construction contractor) resulting in stakeholder and reputational impacts. | Possible | Minor | Medium | 1. Reduce - Ensure that a process is in place whereby the dedicated stakeholder engagement & communications manager reviews communications that will be released by all parties. | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arts facility | Stakeholder risk | If early engagement with local councils does not take place, then there may be delays in obtaining planning approvals, leading to schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - early engagement with the local councils, with schedule & cost contingencies allocated for potential delays. | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arts facility | Planning risk | If inadequate due diligence is performed during site selection, then unexpected remediation or enabling works may be required which results in schedule and cost impacts. | Unlikely | Extreme | High | 1. Reduce - ensure a Site Selection and Acquisition Strategy is prepared, which includes robust due diligence through site investigations. | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arts facility | Planning risk | If land acquisition costs and timelines are not adequately estimated, then there may be additional project delays during the land acquisition phase resulting in cost and schedule impacts. | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. Ensure there is SME involvement for land acquisition estimation work. | yes | yes | yes | yes
Social infrastructure | Arts and recreation | Arts facility | Design inadequacy risk | If the arts facilities operators are not engaged earlier on, then critical operational elements (e.g. loading docks and onsite storage areas) may not be included in the design resulting in operational and stakeholder impacts. | Possible | Major | High | 1. Reduce - ensure operational requirements are captured early on in the design phase through engagement with potential operators, as well as consultation with SMEs experienced in Arts facility development. | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Planning risk | If there are environmental conditions surrounding the existing structure and proposed construction areas that are unexpected (e.g. flora/fauna species, indigenous artefacts, sub-ground conditions etc.) which have not been fully understood, there is a risk of delays and additional costs for issue investigation, and extensive reputational damage. | Possible | Major | High | 1. Reduce - Commission a geotechnical study as early as possible, so as to prevent delivery timeframes being compromised. 2. Reduce - Implement a Stakeholder Engagement Plan that includes early consultation and engagement with the potentially affected indigenous community, once relevant risks have been identified, to see that they are not in conflict with the proposed works 3. Reduce - Undertake an environmental impact study considering impacts on flora & fauna, assess any contamination risks, | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Planning risk | If there are significant variances in vehicle demand to utilise bridge infrastructure due to inaccurate data modelling, there is a risk of ineffective utilisation of infrastructure, and potential for future design changes resulting in an increase in infrastructure and maintenance costs. | Possible | Extreme | High | 1. Reduce - Develop an adaptable and scalable solution to meet higher than expected levels of vehicle demand. 2. Reduce - Undertake detailed traffic network modelling in subsequent project stages to increase certainty on future traffic demand. | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Public Safety risk | If there is a lack of safe and amenable spaces on the existing bridge, there is a risk of personal injury to a path user or construction site member, resulting in safety risks and potential delays to project. | Possible | Major | High | 1. Reduce - Engage the contractor to prepare project specific Health, Safety and Environment (HSE) Management Plans, with sufficient detail to cover scenarios related to the site. | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Design inadequacy risk | If there is a lack of understanding of future loading requirements (e.g. light rail, train, freight etc.) for nearby structure, there is a risk of a structural failure resulting in significant maintenance operating costs. | Unlikely | Extreme | High | 1. Reduce - Early in the project (e.g. during the business case phase), engage with operational and industry/asset SMEs to understand long term strategy for asset utilisation and broader network considerations. | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Planning risk | If there is a poor understanding of utility locations around the construction site, there is a risk of complex utility relocations, resulting in increased costs, delays to delivery, and reputational damage to project. | Possible | Major | High | 1. Reduce - Develop third party agreements with utility agencies, seeking their assistance with timely responses to utility identification and relocation request. This may also include engaging and assigning authorised operatives and designated designers with appropriate skill sets within the project team. | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Human-made environmental disaster risk | If there is any disruption to both the groundwater and wellhead protection zones, or poor quality of dewatering processes, there is a risk that local water sources will be contaminated or disrupted, resulting in community dissatisfaction and additional costs and scheduling delays for remediation. | Possible | Major | High | 1. Reduce - Engage the contractor to prepare project specific Health, Safety and Environment (HSE) Management Plans, with sufficient detail to cover scenarios related to the site. 2. Accept - If the disruption to water sources is unable to be managed, allow schedule & cost contingency for any additional pumping and groundwater diversion work required. | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Environmental implications risk | If there is asbestos and hazardous materials found in the existing structure of the bridge, there is a risk of additional work to be conducted on the existing structure prior to construction, resulting in additional cost and scheduling delays. | Possible | Extreme | High | 1. Reduce - engage specialists to inspect the site for asbestos as part of planning. If asbestos is present, then an asbestos management plan must be prepared. 2. Transfer - negotiate a preferred model to transfer asbestos risk allocations to relevant parties. 3. Accept - include sufficient schedule & cost contingency for asbestos removal / management etc.. | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Stakeholder risk | If there is community opposition to the construction of the bridge, there is a risk that design changes would have to occur through community consultation, resulting in impacts to the schedule. | Likely | Moderate | High | 1. Reduce - Implement a Stakeholder Engagement Plan that includes early consultation and engagement with relevant community groups to ensure communications are clear and effective to manage expectations. | yes | yes | yes | yes
Transport | Road | Bridges (Brownfield/Greenfield) | Weather risk | If there is unexpected flooding events, there is a risk that the bridge infrastructure is inundated, resulting in major operational maintenance activities, including impacts to local resident safety and significant maintenance / repair costs. | Rare | Extreme | Medium | 1. Reduce - During design phase, commission a flood assessment and engage with relevant bodies to assess risks of flooding events. Design considerations should identify how bridge infrastructure would be impacted during such events. | yes | yes | yes | yes
Water | Water | Dam | Skilled labour supply risk | If construction resources / contractors with experience in Dam construction are not involved early in the Project, or not available to be involved, then there may be issues encountered during the delivery of the project resulting in cost, schedule and quality impacts. | Possible | Major | High | 1. Reduce - Extend procurement to overseas for organisations who have experience in the construction / delivery of Dam projects. 2. Reduce - Ensure delivery partner has experience in Dam construction projects and include this as a requirement in the tendering process. | yes | yes |  | yes
Water | Water | Dam | Weather risk | If drought conditions are encountered (i.e. climate change impacts), then there may be a disruption to rainfall collection in the catchment resulting in schedule (i.e. delays in commissioning) and operations impacts (i.e. rainfall is insufficient). | Unlikely | Major | Medium | 1. Reduce - Ensure sufficient analysis goes into rainfall levels and the occurrence of drought in the region where the dam is to be constructed. | yes | yes |  | yes
Water | Water | Dam | Stakeholder risk | If early engagement with impacted stakeholders does not take place, then there may be delays encountered in land acquisition (given the need for land for dam construction, including spillway, and the resulting water storage / lake area) resulting in schedule and cost impacts. | Possible | Major | High | 1. Reduce - Plan for site assessment and acquisition very early on in the project. Ensure there is strong engagement with impacted stakeholders. Stakeholder appetite for a sale will have to be assessed, contingency allowed for and compulsory acquisition may be needed. | yes | yes |  | yes
Water | Water | Dam | Environmental policy change risk | If environmental water flow requirements increase during construction then there may be delays encountered in commissioning as the dam may take longer to fill than originally envisaged resulting in schedule and cost impacts. | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. 2. Reduce - Feedback from government agencies may minimise risk of approval conditions being significantly different to design assumptions. Project modelling will need to be adjusted if environmental flow requirements differ from assumptions. | yes | yes |  | yes
Water | Water | Dam | Skilled labour supply risk | If Project Management staff with experience in Dam construction are not part of the Project then there may be issues encountered during the delivery of the project resulting in cost, schedule and quality impacts. | Possible | Major | High | 1. Reduce - Extend recruitment to overseas for personnel who have experience in the delivery of Dam projects. 2. Reduce - ensure delivery partner personnel have experience in Dam construction projects and include this as a requirement in the tendering process. | yes | yes |  | yes
Water | Water | Dam | Stakeholder risk | If relevant state planning bodies and community groups are not consulted early on, then there may be issues and significant delays with obtaining the planning, environmental and statutory approvals required for construction resulting in schedule and cost impacts. | Almost certain | Major | Critical | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. 2. Reduce - project team or vendor team contains personnel who have experience with relevant state based requirements, and experience in liaising with the relevant departments. | yes | yes |  | yes
Water | Water | Dam | Planning risk | If there are unexpected ground conditions (e.g. lack of rock on which to base a foundation) then there may be a need to change the construction approach (e.g. including additional piling) which will result in cost and schedule impacts. | Likely | Moderate | High | 1. Reduce - ensure comprehensive site inspections and a geotechnical study takes place early in the design phase at the latest. | yes | yes |  | yes
Water | Water | Dam | Planning risk | If weather conditions (i.e. dry seasons) are not considered in planning, then weather disruptions may occur during the construction phase resulting in schedule and cost impacts. | Unlikely | Major | Medium | 1. Reduce - early schedule planning ensures construction takes place over dry seasons, with the early decision made as to how many dry seasons are required and an attempt made to expedite construction within the dry season. | yes | yes |  | yes
Water | Water | Desalination plant | Stakeholder risk | If early engagement of stakeholders (impacted by site works) does not take place, then they may refuse access to their property when / if required, or make complaints resulting in stakeholder, reputational and schedule impacts. | Possible | Moderate | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local businesses and community stakeholders. | Yes |  |  | yes
Water | Water | Desalination plant | Planning risk | If planning does not take place sufficiently far in advance (and identifies a list of options), there there will be delays encountered in procuring suitable land given the plant’s particular requirements (e.g. can’t be on top of a cliff, must be close to suitable intake and discharge locations etc) resulting in cost and schedule delays. | Likely | Major | High | 1. Reduce - Develop a list of options and ensure that there is very early engagement with potentially impacted landowners. | Yes |  |  | yes
Water | Water | Desalination plant | Stakeholder risk | If relevant state planning bodies and community groups are not consulted early on, then there may be issues with obtaining the planning, environmental and statutory approvals required for construction and operation resulting in schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. 2. Reduce - project team or vendor team contains personnel who have experience with relevant state based requirements, and experience in liaising with the relevant departments. | Yes |  |  | yes
Water | Water | Desalination plant | Construction risk (engineering and build) | If rock, or other challenging ground conditions, are encountered, then there may be a need to change the construction approach (e.g. including rock excavation) which will result in cost and schedule impacts. | Likely | Moderate | High | 1. Reduce - ensure comprehensive site inspections and a geotechnical study takes place early in the design phase at the latest. | Yes |  |  | yes
Water | Water | Desalination plant | Design inadequacy risk | If the plant’s potential future capacity requirements are not well understood early on, then there is a chance that future expansion cannot take place (due to land constraints) resulting in operational impacts and failure to meet required demand. | Possible | Moderate | Medium | 1. Reduce - ensure modelling into potential future requirements takes place (i.e. based on growth and drought factors for the region being serviced). If possible, acquire adjacent land in advance for future construction / plant expansion. | Yes |  |  | yes
Water | Water | Desalination plant | Planning risk | If the plant’s power and capacity requirements are not well understood early on there may be wider community impacts as a result of the additional power demand on the grid or insufficient grid capacity to enable the plant to be commissioned and operate. | Possible | Moderate | Medium | 1. Reduce - Engage with relevant SMEs to identify energy efficient desalination options for design and power providers to source carbon neutral electricity supply to offset impact of the plant. 2. Reduce - incorporate renewable power into plant design - e.g., hydro generation on the outlet, and solar on building roofs and surrounding land. 3. Reduce - engage with power suppliers early in planning and design process to ensure grid augmentation (if required) is scheduled to meet the construction and commissioning timeline with funding allowed for. | Yes |  |  | yes
Water | Water | Desalination plant | Environmental risk | If the plant’s receiving waters are not scrutinised closely enough, there is a chance that the discharge water quality (i.e. hyper- saline wastewater) could be more significant or detrimental than expected during operations resulting in compliance, operations and maintenance impacts. | Possible | Moderate | Medium | 1. Reduce - Perform detailed analysis on receiving waters and expected impact of plant discharges on these, and engage with relevant state based agencies to understand if there will be any developments in the future (i.e. construction of assets nearby that would impact water quality e.g. an aquaculture development). | Yes |  |  | yes
Water | Water | Desalination plant | Compliance/regulatory risk | If the plant’s source water is not monitored closely enough, there is a chance that the production water quality (i.e. water that goes into supply) changes outside of acceptable parameters could result in compliance, operations and maintenance impacts. | Possible | Moderate | Medium | 1. Reduce - Engage with relevant state based agencies to understand if if there will be any developments in the future (i.e. construction of assets nearby that can impact water quality e.g. port development handling hazardous materials such as fuels or chemicals). | Yes |  |  | yes
Energy | Gas | Gas pipelines (Greenfield/Brownfield) | Schedule risk | If construction takes longer than expected and timelines agreed with customers to facilitate tie-ins are too short, then there can be delays in resuming services resulting in contract breaches and reputational impacts. | Possible | Moderate | Medium | 1. Accept - Engage with customers early on to understand how long supply can be cut off for and negotiate timelines with enough contingency given the complexity associated with brownfield work. | yes | yes | yes | yes
Energy | Gas | Gas pipelines (Greenfield/Brownfield) | Supply chain risk | If materials handling during transport and storage is not adequate, then there is a risk that materials are either damaged during transit or onsite resulting in quality, cost and schedule impacts. | Likely | Minor | Medium | 1. Reduce - ensure there is sufficient schedule contingency (e.g. shipments of materials such pipes should commence before construction starts, with a key materials onsite for start of construction). Through this, identification of defects can take place early on, allow additional ordering of spare parts in advance and ensure that storage areas (e.g. pipe yards) are ready as contingency. 2. Reduce - ensure there is a structured and resource based inspection test plan which involves inspection of materials upon arrival on site. 3. Reduce - ensure there is appropriate asset storage with a robust materials handling processes in place. | yes | yes | yes | yes
Energy | Gas | Gas pipelines (Greenfield/Brownfield) | Planning risk | If potential future transmission capacity requirements are not adequately captured and considered in design, then future commercial opportunities will be missed due to pipeline constraints resulting in financial impacts. | Unlikely | Major | Medium | 1. Reduce - consult early on with the business development / commercial team to understand potential future commercial opportunities. Ensure that these requirements are agreed broadly and reflected in requirements and designs. | yes | yes | yes | yes
Energy | Gas | Gas pipelines (Greenfield/Brownfield) | Compliance/regulatory risk | If relevant state based land access requirements are not well understood early on, then there may be delays in obtaining access to land (e.g. ROW, road and rail crossings, private lands, utilities) leading to schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - ensure the stakeholder engagement plan captures required engagement with relevant government agencies and that this activity takes place early on. 2. Reduce - project team or vendor team contains personnel who have experience with relevant state based requirements, and experience in liaising with the relevant departments or agencies. | yes | yes | yes | yes
Energy | Gas | Gas pipelines (Greenfield/Brownfield) | Stakeholder risk | If stakeholder opposition to the project is not understood early on, then there may be opposition encountered whilst trying to obtain approvals for gas pipeline infrastructure resulting in cost and schedule impacts. | Possible | Minor | Medium | 1. Reduce - ensure that a stakeholder engagement plan has been produced and captures relevant protest groups or individuals with plans in place to engage with them. | yes | yes | yes | yes
Energy | Gas | Gas pipelines (Greenfield/Brownfield) | Operational risk | If the asset operations team is not sufficiently involved during planning, design and construction, then there may be operations and maintenance issues post handover resulting in operational, reputation and financial risks. | Possible | Moderate | Medium | 1. Reduce - ensure the operations team has a an active role on the project team / governance committee, with appropriate input into planning, design, oversight across key phases, and input into the practical completion decision. 2. Reduce - ensure operations planning is completed early on, there is a structured checklist to tracking operational readiness. | yes | yes | yes | yes
Energy | Gas | Gas pipelines (Greenfield/Brownfield) | Project management risk | If vendor quality obligations are not well communicated and contractually enforced, then integrity issues (e.g. pipeline leak / rupture or loss of containment) may emerge during hydrotesting resulting in potential cost, schedule and quality impacts. | Unlikely | Major | Medium | 1. Reduce - ensure strong quality obligations are in place for vendors and contractors and are enforced (aligned to Australian Standards at a minimum). 2. Reduce – ensure a fit for purpose Quality Management Plan is in place, which includes activities such as pipeline testing, QA/QC, hydro tests, leak detection systems etc. 3. Reduce - ensure there is schedule and cost contingency to remediate any integrity issues. | yes | yes | yes | yes
Energy | Gas | Gas pipelines (Greenfield/Brownfield) | Planning risk | If weather conditions (i.e. wet seasons) are not considered in project planning / operational use, then weather disruptions may occur during the construction phase (or in operations) resulting in schedule and cost impacts, and limitations in being able to achieve benefits. | Unlikely | Major | Medium | 1. Reduce - early schedule planning ensures construction takes place over the dry season, with the early decision made on contingency options if project progress is impacted by weather conditions. The schedule should also have appropriate provisions to accommodate seasonality. | yes | yes | yes | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Design inadequacy risk | If early design work does not consider emerging technology / contemporary models of clinical care, or does not align to clinical practice / stakeholder requirements, then the hospital’s design may be sub-optimal resulting in operational impacts. | Unlikely | Major | Medium | 1. Reduce - engage with relevant SMEs to identify areas for innovation early on to input into design. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Stakeholder risk | If environmental impacts from building works (e.g. dust and noise) are not considered, then there may be complaints received from the surrounding neighbourhood, resulting in potential reputational and stakeholder impacts. | Likely | Minor | Medium | 1. Reduce - Establish environmental control processes and procedures in place that are rolled out early in collaboration with the contractor. This should also include consideration to environmental controls required post operationalisation. Ensure this consideration has been taken on board in the stakeholder engagement plan and design considerations. 2. Reduce - Commission environmental studies throughout the course of the project to ensure the noise and vibration pollution can be controlled. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Planning risk | If existing service mains and other utilities are not identified early on with communication of when works around the mains will happen, then there may be a disruption to critical clinical services resulting in operational and safety impacts. | Unlikely | Extreme | High | 1. Reduce - consult with utilities partners to ensure utilities are not disrupted (e.g. power supply), with careful sequencing of works. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Planning risk | If handover and commissioning processes are not conducted properly, then there may be staff frustration and even life threatening implications on Day One, resulting in reputational and operational impacts. | Unlikely | Extreme | High | 1. Reduce - Ensure that there are no defects at completion (this includes ICT related issues) to ensure there is a fault free operational commissioning phase. Ensure there is an early commissioning focus, with early engagement of operational staff (e.g. site visits to respective departments) and their input into practical completion decision making. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Planning risk | If it is an older hospital, then this is a risk that Asbestos is present, resulting in the potential for contaminant and contamination issues and impacts on safety, costs and time. | Unlikely | Major | Medium | 1. Reduce - engage specialists to inspect the site for asbestos as part of planning. If asbestos is present, then an asbestos management plan must be prepared. 2. Transfer - negotiate a preferred model to transfer asbestos risk allocations to relevant parties. 3. Accept - include sufficient schedule & cost contingency for asbestos removal / management etc. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Financial/cost/budget risk | If operational costs are not adequately considered during the design phase, then parts of the hospital may be too expensive to operate resulting in operational impacts (e.g. closure of certain hospital sections). | Possible | Major | High | 1. Reduce - perform asset management / service planning early on to ensure that operational costs are understood early on. Engage with relevant operations partner to ensure the planning fits their available budget. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Stakeholder risk | If the adjoining facilities (e.g. operating theatres) operational stakeholders are not informed / consulted, there may be disruptions to normal operations whilst structural work is carried out resulting in stakeholder, operational and reputational impacts. | Possible | Major | High | 1. Reduce - ensure potential operational impacts are well understood in the start through stakeholder consultation with the site’s operations team. This includes considerations towards contingency planning for any disruptions early in the project lifecycle. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Planning risk | If the existing hospital site had not considered accessibility requirements in the planning and design phases, then there is a risk of scope creep as any changes to existing facilities may require additional works to ensure these facilities remain compliant with accessibility standards (NCC or DDA), resulting in cost overruns and schedule delays. | Possible | Major | High | 1. Reduce - commission accessibility studies of existing facilities early in the project planning to identify any areas of non-compliance and consider how these may need rectification as part of project delivery. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Stakeholder risk | If the local indigenous community is not consulted during the design phase, then the design and provision of spaces may not align with ‘design with country’ and are culturally insensitive resulting in stakeholder / user disengagement impacts with the local community. | Possible | Moderate | Medium | 1. Reduce - Establish an Indingenous community working group, and consult with the group regularly throughout the lifecycle of the project. Also specifically engage with local community needs to understand their needs and plan and design accordingly. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Stakeholder risk | If the scope of the brownfield hospital is not made clear to all stakeholders involved, there may be additional refurbishment related requests resulting in schedule and cost impacts. | Likely | Moderate | High | 1. Reduce - careful stakeholder management during planning and construction, with explicit socialisation on the extent of refurbishment work on the brownfield site. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Planning risk | If there is inaccurate analysis of existing site structural integrity or relevant site services in design development (e,g. changing use of wards), then there is a risk the existing structures cannot cope with the new loads or the services are not upgraded as required, resulting in long term operations and maintenance impacts and non-compliance with NCC requirements. | Possible | Extreme | High | 1. Ensure NCC requirements have been explicitly considered in the design development, and appropriate expertise is sourced to support relevant analysis of repurposing of buildings. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Addon/Brownfield) | Stakeholder risk | If there is poor engagement with Indigenous and European communities, there is a risk that heritage sites are not fully understood and are adversely impacted during construction activities, leading to schedule delays and reputational damage to the project. | Possible | Major | High | 1. Reduce - establish a dialogue with local Indigenous communities,and develop a Cultural Heritage Management Agreement / Plan which details how cultural heritage impacts will be considered throughout project delivery. 2. Reduce - Engage a Heritage Consultant (Aboriginal and European Heritage), Ecologist and Town Planner as part of project initiation to ensure these impacts have been identified and considered. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Design inadequacy risk | If early design work does not consider emerging technology / contemporary models of clinical care (i.e. within the whole of hospital planning strategy), or does not align to clinical practice / stakeholder requirements, then the hospital’s design may be sub-optimal resulting in operational impacts. | Unlikely | Major | Medium | 1. Reduce - engage with relevant SMEs to identify areas for innovation early on to input into design. Establish key planning principles and models of care / patient flows / patient centric care principles (at the department / user group level) which are endorsed at the Executive level prior to commencing user group consultation for functional briefs. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Stakeholder risk | If environmental impacts from building works (e.g. dust and noise) are not considered, then there may be complaints received from the surrounding neighbourhood, resulting in potential reputational and stakeholder impacts. | Likely | Minor | Medium | 1. Reduce - Establish environmental control processes and procedures in place that are rolled out early in collaboration with the contractor. This should also include consideration to environmental controls required post operationalisation. Ensure this consideration has been taken on board in the stakeholder engagement plan and design considerations. 2. Reduce - Commission environmental studies throughout the course of the project to ensure the noise and vibration pollution can be controlled. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Planning risk | If handover and commissioning processes are not conducted properly, then there may be staff frustration and even life threatening implications on Day One, resulting in reputational and operational impacts. | Unlikely | Extreme | High | 1. Reduce - Ensure that there are no defects at completion (this includes ICT related issues) to ensure there is a fault free operational commissioning phase. Ensure there is an early commissioning focus, with early engagement of operational staff (e.g. site visits to respective departments) and their input into practical completion decision making. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Planning risk | If inadequate due diligence is performed during site selection, then unexpected remediation or enabling works may be required which results in schedule and cost impacts. | Unlikely | Extreme | High | 1. Reduce - ensure a Site Selection and Acquisition Strategy is prepared, which includes robust due diligence through site investigations, and testing the various master plan typologies developed during the master planning exercise. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Financial/cost/budget risk | If operational related costs are not adequately considered during the design phase, then parts of the hospital may be too expensive to operate resulting in operational impacts (e.g. closure of certain wards / sections of the hospital). | Possible | Major | High | 1. Reduce - perform asset management / service planning early on to ensure that operational costs are understood early on. Engage with relevant operations partner to ensure the planning fits their available budget. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Planning risk | If planning and preparation works do not effectively establish the previous use of the site e.g. mining, agriculture, then there is a risk that the site is contaminated, resulting in additional decontamination works, reputational damage, cost overruns and schedule delays. | Possible | Extreme | High | 1. Reduce - ensure a Site Selection and Acquisition Strategy is prepared, which includes robust due diligence through site investigations. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Stakeholder risk | If the local indigenous community is not consulted during the design phase, then the design and provision of spaces may not align with ‘design with country’ and are culturally insensitive resulting in stakeholder / user disengagement impacts with the local community. | Possible | Moderate | Medium | 1. Reduce - Establish an Indigenous community working group, and consult with the group regularly throughout the lifecycle of the project. Also specifically engage with local community needs to understand their needs and plan and design accordingly. | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Design inadequacy risk | If the project design does not consider appropriate transport connectivity (bus routes), kiss and drop facilities, car parking and accessibility requirements, then there there may be traffic impacts causing congestion once the hospital is operational, resulting in frustration and reputational damage to the project / State from the hospital staff, patients and local community. | Possible | Minor | Medium | 1. Reduce - Consider options for the hospital to develop detailed ‘Green Travel Plans’ for staff outlining all public and active transport opportunities and strategies by which to reduce private vehicle travel to the site. 2. Reduce - Ensure there are relevant stakeholders engaged in the design phase (e.g. urban planning, local community stakeholders, Hospital / Health representatives etc.) | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Operational risk | If there is a lack of detailed workforce planning, there is a risk that the hospital is unable to secure a sustainable workforce (capability and capacity for various clinical specialty needs) into the future, resulting in safety risks extended operations and maintenance costs once operational. | Likely | Extreme | Critical | 1. Reduce - Develop a comprehensive workforce plan / framework that: -Establishes changes in workforce requirements -Outlines sustainable recruitment and retention strategies -Has a supportive learning and development framework, and -Identifies existing and new /potential education partnerships | yes | yes |  | yes
Social infrastructure | Health | Hospital (Greenfield) | Operational risk | If workforce planning has not been considered as part of project planning, then there may be issues in building out staff capacity and capability once the site is ready resulting in operational and reputational impacts. | Possible | Major | High | 1. Reduce - develop a comprehensive workforce plan that establishes workforce requirements, outlines sustainable recruitment and retention strategies, has a supportive learning and development framework and identifies existing and new / potential education partnerships. | yes | yes |  | yes
Transport | Rail | Level crossing | Construction risk (engineering and build) | If there are changes to engineering standards during the course of the project, there is a risk of rework required to existing designs / construction activity (or a need to seek waivers from relevant bodies), resulting in schedule delays and cost overruns. | Rare | Major | Low | 1. Reduce - Establish a process to engage with regulatory bodies throughout project delivery to ensure any expected changes to engineering standards are flagged early, and can be planned within contingency scenarios. | yes | yes |  | yes
Transport | Rail | Level crossing | Operational risk | If there are extended delays of train station unavailability due to construction activity, there is a risk of a change in patron behaviour away from public transport, resulting in long-term bus and rail patronage being lost, and a long-term reduction in fare revenue (impacting benefits realisation). | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / community bodies. This engagement should clarify expected downtime and benefits of the project to help maintain patronage volumes post project. | yes | yes |  | yes
Transport | Rail | Level crossing | Construction risk (engineering and build) | If there is a lack of clarity on the technical / engineering standards and network integrity controls between project team members and contractors, there is a risk that project deliverables are misaligned from the technical standards, leading to rework / remediation activities, with schedule delays and cost overruns. | Unlikely | Major | Medium | 1. Reduce - Engage with regulatory bodies (or technical engineering experts) throughout project delivery to ensure alignment with engineering standards, and can be planned within contingency scenarios. | yes | yes |  | yes
Transport | Rail | Level crossing | Benefits realisation risk | If there is no clear vision for the transport network's future technical needs, there is a risk that this project's outcomes are misaligned, leading to extended operations and maintenance costs (and potential costs for future projects) to remediate outcomes to align to the future strategy. | Possible | Major | High | 1. Reduce - As part of the business case approval, ensure that the objectives and intended outcomes of the project are agreed across key senior stakeholders across the industry (incl. Ministerial). This may also include engagement with stakeholders within the State / Federal Transport Depts. | yes | yes |  | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Stakeholder risk | If environmental and light rail experts are not engaged through project planning and design, there is a risk that (once operational) the light rail causes unacceptable impacts (e.g. noise, vibration, safety, aesthetics), leading to community dissatisfaction and requirements to complete remedial works, resulting in project cost overruns and reputational damage to the project. | Possible | Extreme | High | 1. Reduce - Establish environmental control processes and procedures in place that are rolled out early in collaboration with the contractor. This should also include consideration to environmental controls required post operationalisation. Ensure this consideration has been taken on board in the stakeholder engagement plan and design considerations. 2. Reduce - Commission environmental studies throughout the course of the project to ensure the noise and vibration pollution can be controlled. | yes | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Planning risk | If potential future uses of the asset (e.g. driverless rolling stock) / broader transport network requirements (e.g. integration with rail) are not considered or planned for, there is a risk of misalignment with surrounding infrastructure, resulting in future operational and reputational impacts. | Possible | Extreme | High | 1. Reduce - Early in the project (e.g. during the business case phase), engage with operational and industry/asset SMEs to understand long term strategy for asset utilisation and broader network considerations. | yes | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Public Safety risk | If the pedestrian signalling and protection infrastructure is ineffective, there is a risk of pedestrians walking in the path of the light rail, resulting in civilian injury and possible fatality. | Possible | Extreme | High | 1. Reduce - As part of project design, consider key controls such as a Train Control Systems which will automate the limits on light rail speed and introduce signals passed danger. 2. Reduce - Engage with relevant Rail Safety experts (e.g. Rail Industry Safety and Standards Board) as part of project inception in order to consider potential infrastructure controls within design. | yes | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Human-made environmental disaster risk | If there are accidental spills during construction activities, given the proximity of construction works to nearby watercourses, drainage systems and receiving catchments, there is a risk of adverse impacts on water quality, leading to environmental risks for the broader community, and reputational damage to the project. | Unlikely | Extreme | High | 1. Reduce - Engage the contractor to prepare project specific Health, Safety and Environment (HSE) Management Plans, with sufficient detail to cover scenarios related to the site. | yes | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Construction risk (engineering and build) | If there are inaccuracies in historical record keeping, then there may be crossings or clashes with existing underground utilities (e.g.other pipes, gas lines, voltage or optic fibre cables) resulting in schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - allow time for early works services searching and potholing beforehand and utilise non-destructive digging equipment and techniques. 2. Accept - allow cost and schedule contingency for the discovery, and relocation, of utilities. 3. Transfer - consider options to allocate risk sensibly to contractors. | yes | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Operational risk | If there are ineffective controls in place to limit overspeed and provide signalling of passed danger, there is a risk of light rail derailment and collisions, resulting in damage to assets and civilian injury and possible fatality. | Possible | Extreme | High | 1. Reduce - As part of project design, consider key controls such as a Train Control Systems which will automate the limits on light rail speed and introduce signals passed danger. | yes | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Planning risk | If there is a lack of integrated planning across the transport network and other modes / connecting public transport, there is a risk that the designed light rail routes do not align to other infrastructure projects and routes in the neighbouring areas, resulting in ineffective utilisation of government funds, and lead to additional operations and maintenance costs (including potential for future projects). | Unlikely | Extreme | High | 1. Reduce - Complete consultation / process mapping with key stakeholders (e.g. road authorities, respective transport authorities) to ensure any risks related to interfaces are identified and considered as part of design. 2. Reduce - Document all known interfaces / dependencies across work packages and projects, and establish a cross work package / cross project dependency management forum in order to track and govern these dependencies through project delivery. | yes | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Governance risk | If there is an ineffective contract model established between the Owner, principal contractor and relevant subcontractors, there is a risk of privity issues with claims between the principal contractor and relevant subcontractors and damage to the operating relationship between these parties, leading to schedule delays and cost overruns. | Possible | Major | High | 1. Transfer - Consider privity issues in contract delivery model and transfer risk to relevant contractors / subcontractors where possible. E.g. establish a chain of contracts where the principal contractor is the lead, and owns/shares risks with their subcontractors. | yes | yes
Transport | Rail | Light rail (Greenfield/Brownfield) | Planning risk | If there is poor urban planning to inform site selection and design phases for infrastructure, there is a risk that design requirements such as clearance near a rail corridor or public transport connectivity may not have been appropriately considered, resulting in the site being accessibility issues, reputational damage and long term operations and maintenance costs for remedial works. | Possible | Extreme | High | 1. Reduce - Develop a structured stakeholder management plan and communications plan, which includes early engagement with relevant urban planning representatives, as well as relevant local residents and community stakeholders. | yes | yes
Transport | Road | Low use road | Planning risk | If a dilapidation survey of existing public roads is not conducted with sufficient detail prior to commencement of construction, then there is a risk that road / asset decay during construction may be associated with the project’s construction, resulting in reputational damage, and cost overruns to support additional remedial works. | Likely | Moderate | High | 1. Reduce - Commission a detailed Dilapidation Survey prior to construction activity, and ensure this is reviewed and approved by site staff and relevant contractors to use as a source of truth of site conditions. | yes | yes | yes | yes
Transport | Road | Low use road | Asset Management risk | If road authorities are reactive in their approach to road maintenance and lack a formal strategy for road maintenance, then there there is a risk of increased maintenance costs, resulting in financial loss and safety issues for road users. | Likely | Minor | Medium | 1. Reduce - Establish and agree an Asset Maintenance Plan which details relevant assets and their associated maintenance activities, including estimated cost and frequency. This should also clearly define roles and responsibilities relating to asset management activity. | yes | yes | yes | yes
Transport | Road | Low use road | Design inadequacy risk | If road condition data is collected using visual surveying, then there is a risk that the results are unreliable due to human error, leading to quality and safety issues on the asset. | Likely | Moderate | High | 1. Reduce - Support visual surveying activities with detailed data modelling, which can be used to validate visual surveys to enhance the accuracy of decision making. | yes | yes | yes | yes
Transport | Road | Low use road | Compliance/regulatory risk | If there are unclear or out of date acceptance criteria across each aspect of project deliverables (including specific areas of construction such as concrete slabs and walls), there is a risk of disputes between contractors relating to defect remediation requirements, resulting in schedule delays and potential cost overruns. | Possible | Major | High | 1. Reduce - Ensure that the Owner has a clear Quality Management Plan which details specific acceptance criteria and sign off points. Ensure that these sign off points are from the Owner’s team (i.e. not one of the contractors). 2. Reduce - Ensure that if there are requirements to be enacted in the future, there should be provisions within contracts to enable the acceptance criteria to be updated from time to time during the course of the contract. | yes | yes | yes | yes
Transport | Road | Low use road | Stakeholder risk | If there is are ineffective stakeholder management processes to engage the community, councils and other relevant stakeholders, there is a risk of disconnect between project outcomes and community expectations, leading to potential rework to project deliverables, reputational damage and schedule overruns. | Possible | Minor | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / community groups. | yes | yes | yes | yes
Transport | Road | Low use road | Design inadequacy risk | If there is insufficient consideration of how the new road will integrate with existing periphery road infrastructure, there is a risk of misalignment of designs, resulting in reputational damage, cost overruns and schedule delays (driven by remedial works). | Possible | Major | High | 1. Reduce - Commission site surveys to complete analysis of peripheral road environment and existing infrastructure during early planning to ensure these aspects are considered in project design. | yes | yes | yes | yes
Transport | Road | Low use road | Asset Management risk | If there is unreliable data about roads (including cost and road condition), then there is a risk that projects / councils are unable to make evidence-based decisions relating to asset maintenance, resulting in increased long term maintenance costs. | Possible | Moderate | Medium | 1. Reduce - Establish a process to reassess road use and condition modelling and validate assumptions as the project progresses. 2. Reduce - Support data modelling activities with site surveillance to validate modelling at specific points in time during asset life. | yes | yes | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Benefits realisation risk | If project modelling and associated designs are not developed with future risks / demand trends in mind, there is a risk that project requirements are underestimated (e.g. implications of passenger services, unidentified 3rd party works, facilitating works to minimise service disruptions during future system upgrade/augmentation), resulting in significant operations and maintenance costs for additional remedial works. | Possible | Major | High | 1. Reduce - Establish a process to reassess project modelling and validate assumptions as the project progresses. This may also include completing sensitivity analysis over variations to the modelling to consider contingency planning. 2. Accept - Consider appropriate risk allowances in business case and benefits realisation plan based on the sensitivity analysis. | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Skilled labour supply risk | If there are poor resource management plans in place across the project team and the contractor’s team, there is a risk of inabilities to select and retain key project personnel (particularly those SMEs with expertise in rail maintenance and upgrades), leading to lower quality project delivery, increased defects and increasing operations and maintenance costs. | Possible | Moderate | Medium | 1. Reduce - Develop a Resource Management Plan which includes stipulation of personnel experience requirements across key suppliers. Where possible, establish succession plans with longer term projects to ensure that each party’s key expertise remain committed and in place to support the project. | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Benefits realisation risk | If there is inaccurate data used as part of the project business case and planning / design phases, there is a risk that the project benefits can be overstated and the agreement to a project outcome which may not cater for current or future needs / trends, resulting in an inefficient use of investment funds, and inability to realise benefits. | Unlikely | Extreme | High | 1. Reduce - Establish a Benefits Management Plan which includes a process to reassess benefits modelling and validate assumptions as the project progresses. This may also include completing sensitivity analysis over variations to the modelling to consider contingency planning. | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Benefits realisation risk | If there is inaccurate modelling of expected demand levels on train routes, there is a risk of poor utilisation, resulting in lower revenues, lower benefit-cost ratio (BCR), resulting in cost impacts (i.e. inefficient use of project funds). | Possible | Major | High | 1. Reduce - Establish a process to reassess demand modelling and validate assumptions as the project progresses. This may also include completing sensitivity analysis over variations to the modelling to consider contingency planning. 2. Accept - Consider appropriate risk allowances in business case and benefits realisation plan based on the sensitivity analysis. | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Construction risk (engineering and build) | If there is inaccurate or insufficient information provided to the contractor (principal supplied information, any site surveys available and inspection results prior to the commencement date), there is a risk of misalignment between design, construction and built tracks and stakeholder expectations, resulting in significant operations and maintenance costs for additional remedial works. | Possible | Major | High | 1. Transfer - Ensure contractual documentation requires contractors to complete their own due diligence relating to information provided to them. 2. Reduce - Ensure there is appropriate opportunity for the contractor to engage with relevant operational staff to ensure any ambiguous areas can be clarified. 3. Reduce - Develop a structured stakeholder management plan, which includes engagement with key internal project stakeholders.. | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Stakeholder risk | If there is poor engagement with Indigenous and European communities, there is a risk that heritage sites are not fully understood and are adversely impacted during construction activities, leading to schedule delays and reputational damage to the project. | Possible | Major | High | 1. Reduce - establish a dialogue with local Indigenous communities,and develop a Cultural Heritage Management Agreement / Plan which details how cultural heritage impacts will be considered throughout project delivery. 2. Reduce - Engage a Heritage Consultant (Aboriginal and European Heritage), Ecologist and Town Planner as part of project initiation to ensure these impacts have been identified and considered. | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Governance risk | If there is poor governance, decision making and clarity on project milestones / benefits, there is a risk that the staging of the project is based on stakeholder priorities, rather than being driven through a risk based approach (or an alternative approach to maximise benefits), resulting in greater exposure to schedule delays and limitations in optimising project benefits. | Possible | Major | High | 1. Reduce - As part of project mobilisation, establish a Project Governance Framework and clear Terms of References for relevant governance forums to ensure there is clarity relating to project decision making. This should include endorsement of key project documents, strategies, budgets, scope and escalation process. | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Governance risk | If there is poor management and structuring of the complex interfaces between work packages (e.g. station, tunnel, rail) or with other projects with concurrent timeframes (e.g. relocation of assets / utilities), there is a risk that each of the projects progress at various paces, resulting in key misalignment between work package and project commissioning milestones, leading to project schedule delays. | Likely | Major | High | 1. Reduce - Document all known dependencies across work packages and projects, and establish a cross work package / cross project dependency management forum in order to track and govern these dependencies through project delivery. 2. Reduce - Where possible, ‘pre-ascertain’, ‘pre-determine’ and ‘pre-agree’ a daily rate with contractors whereby a delay with their specific workstreams result in penalties. | yes | yes
Transport | Rail | Main line works (Greenfield/Brownfield) | Governance risk | If there is poor management of the complex interfaces between work packages (or with other projects with concurrent time frames - e.g. relocation of assets / utilities), there is a risk that each of the projects progress at various paces, or work is doubled up across projects, resulting in key misalignment between work package and project commissioning milestones, leading to community dissatisfaction and schedule delays. | Possible | Major | High | 1. Reduce - Document all known dependencies across work packages and projects, and establish a cross work package / cross project dependency management forum in order to track and govern these dependencies through project delivery. 2. Reduce - Where possible, consider co-locating / sharing resources across projects / work packages to help identify and manage interfaces between the various projects / packages. | yes | yes
Social infrastructure | Justice | Prison/Correctional centre | Stakeholder risk | If industry groups and union representatives are not appropriately consulted or engaged throughout the project, then industrial action may occur from existing correctional staff or project team members, resulting in the provision of services ceasing and schedule delays. | Unlikely | Major | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant industry groups and representatives. 2. Accept - Consider appropriate contingency if industry action takes place. | yes | yes |  | yes
Social infrastructure | Justice | Prison/Correctional centre | Stakeholder risk | If local community and stakeholder expectations regarding a prison or correctional centre, such as location, are not considered throughout the project, then local communities and stakeholders will feel unheard or unconsulted resulting in reputational damage to the project and schedule delays. | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local communities and stakeholders. | yes | yes |  | yes
Social infrastructure | Justice | Prison/Correctional centre | Stakeholder risk | If relevant government planning bodies and community groups are not consulted appropriately, then there is a risk planning, environmental and statutory approvals are not received for development or redevelopment as per the project schedule or that the approval conditions are received late, resulting in cost overruns and schedule delays. | Unlikely | Major | Medium | 1. Reduce - Integrate key deadlines for submitting and receiving approval in the project schedule. 2. Reduce - Develop a stakeholder management plan, which includes early engagement with relevant local/state planning bodies. 3. Transfer - Develop a matrix of all required approvals and consider allocating risk to relevant contractors to obtain approval. | yes | yes |  | yes
Social infrastructure | Justice | Prison/Correctional centre | Compliance/regulatory risk | If there is a change in legislation or mandatory policy after commencement of the project, then there is a risk that aspects of the project will need to be altered, resulting in impacts to costs, time and scope. | Rare | Extreme | Medium | 1. Reduce - Identify all relevant and applicable legislation and mandatory law to ensure, if changes are made, they are efficiently applied or incorporated. 2. Transfer - Negotiate with proponents to share / accept risks associated with legislative or policy changes. 3. Accept - Consider appropriate contingency in project plan and budget. | yes | yes |  | yes
Social infrastructure | Justice | Prison/Correctional centre | Asset Management risk | If there is a lack of formal strategy or authorities are reactive in their approach to prison maintenance, reinstatement, replacement and refurbishment requirements, there is a risk of facilities deteriorate at a faster pace, resulting in increased operations and maintenance costs. | Likely | Moderate | High | 1. Reduce - Develop a formal strategy for maintenance, reinstatement, replacement and refurbishment requirements of assets. 2. Transfer - Negotiate a preferred model to transfer risk allocations to relevant parties. 3. Accept - Consider appropriate allowances in prison maintenance budgets. | yes | yes |  | yes
Social infrastructure | Justice | Prison/Correctional centre | Stakeholder risk | If there is insufficient time allocated or poor engagement between the proponents and operational staff, then there is a risk that designs and construction plans are inadequate or incomplete, resulting in additional costs due to remedial works of the design and resolution of defects. | Likely | Major | High | 1. Reduce - Allocate sufficient time to undertake design briefings with contractor to ensure detailed designs are provided to inform construction plans. 2. Transfer - Negotiate with proponents to share / accept risks associated with designs. 3. Accept - Consider appropriate contingency for construction plans and project budget. | yes | yes |  | yes
Social infrastructure | Education | School (Brownfield) | Planning risk | If construction occurs during the school term, then there can be outages and construction works causing disruption to classes, resulting in an interruption to students' education and activities and potential reputational damage to the project. | Possible | Minor | Medium | 1. Reduce - consult with utilities partners to ensure utilities are not disrupted (e.g. power supply), with careful sequencing of works. 2. Reduce - As part of project planning, ensure sequencing of works minimises disruption to classes (i.e. construction activity which causes noise disruption should be avoided around school exam periods). 3. Reduce - engage with the school staff in advance and provide communications on when potential outages / noise disruption may occur. | yes | yes | yes | yes
Social infrastructure | Education | School (Brownfield) | Planning risk | If it is an older school, then this is a risk that Asbestos is present, resulting in the potential for contaminant and contamination issues and impacts on safety, costs and time. | Unlikely | Major | Medium | 1. Reduce - engage specialists to inspect the site for asbestos as part of planning. If asbestos is present, then an asbestos management plan must be prepared. 2. Transfer - negotiate a preferred model to transfer asbestos risk allocations to relevant parties. 3. Accept - include sufficient schedule & cost contingency for asbestos removal / management etc. | yes | yes | yes | yes
Social infrastructure | Education | School (Brownfield) | Planning risk | If the existing school site had not considered accessibility requirements in the planning and design phases, then there is a risk of scope creep as any changes to existing facilities may require additional works to ensure these facilities remain compliant with accessibility standards (NCC or DDA), resulting in cost overruns and schedule delays. | Possible | Major | High | 1. Reduce - commission accessibility studies of existing school facilities early in the project planning to identify any areas of non-compliance and consider how these may need rectification as part of project delivery. | yes | yes | yes | yes
Social infrastructure | Education | School (Brownfield) | Planning risk | If there are inaccuracies in historical record keeping, then there may be crossings or clashes with existing utilities (e.g.other pipes, voltage or optic fibre cables) resulting in schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - allow time for services searching and potholing beforehand and utilise non-destructive digging equipment and techniques. 2. Accept - allow cost and schedule contingency for the discovery, and relocation of utilities. | yes | yes | yes | yes
Social infrastructure | Education | School (Brownfield) | Procurement risk | If there are inadequate procurement processes and due diligence checks prior to construction commencement, there construction workers may not have had appropriate clearance or background checks relating to working in spaces with children, resulting in a safety risks to students and safety and reputational impacts. | Possible | Extreme | High | 1. Reduce - ensure that a working for children check is included in all agreements with contractors and subcontractors as a mandatory requirement. | yes | yes | yes | yes
Social infrastructure | Education | School (Brownfield) | Construction workplace safety risk | If there are trees on the school site, then they may not be adequately protected during construction, resulting in potential alterations to the soil grade meaning trees are damaged during the construction phase, resulting in trees dying, branches or the tree itself falling into playgrounds, posing a safety risk to those around the construction site (workers, students, teachers etc). | Possible | Extreme | High | 1. Reduce - identify and document the location of all trees on the school site prior to commencement. 2. Reduce - engage a project arborist and conduct construction works in accordance with AS4970-2009. | yes | yes | yes | yes
Social infrastructure | Education | School (Brownfield) | Planning risk | If there is inaccurate analysis of existing site structural integrity or relevant site services in design development (e,g. changing use of classrooms), then there is a risk the existing structures cannot cope with the new loads or the services are not upgraded as required, resulting in long term operations and maintenance impacts and non-compliance with NCC requirements. | Possible | Extreme | High | 1. Ensure NCC requirements have been explicitly considered in the design development, and appropriate expertise is sourced to support relevant analysis of repurposing of buildings. | yes | yes | yes | yes
Social infrastructure | Education | School (Brownfield) | Stakeholder risk | If there is poor engagement with Indigenous and European communities, there is a risk that heritage sites are not fully understood and are adversely impacted during construction activities, leading to schedule delays and reputational damage to the project. | Possible | Major | High | 1. Reduce - establish a dialogue with local Indigenous communities,and develop a Cultural Heritage Management Agreement / Plan which details how cultural heritage impacts will be considered throughout project delivery. 2. Reduce - Engage a Heritage Consultant (Aboriginal and European Heritage), Ecologist and Town Planner as part of project initiation to ensure these impacts have been identified and considered. | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Weather risk | If consideration is not given to proofing against environmental risks associated with the project (such as bushfire prone area or building on a floodplain) during the design process, then there is a risk the site is not prepared or protected against such risk, resulting in potential for extensive damage and impacts to the safety of users of the site. | Rare | Extreme | Medium | 1. Reduce - Engage with regulatory bodies to ensure there is clarity on required controls (e.g. installation of fire hydrants, tree proximity to overhead electrical transmission lines). 2. Reduce - Develop and implement a proposed stormwater concept plan and erosion and sediment control plan. | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Population/demographics risks | If current and future demographic trends (population growth, priority catchment areas etc.) are not considered in site selection, then there is a risk that the demand for the school is inaccurate, resulting in low utilisation of the infrastructure and operational and reputational impacts. | Possible | Major | High | 1. Reduce - Early in the project (e.g. during the business case phase), engage with industry SMEs and urban planning to understand long term demographic / population growth modelling in order to inform the site selection and expected students. This may be where new subdivisions of property or where existing schools are at capacity without expansion options, and will also help to inform other requirements for the school (e.g. transport connectivity etc.) | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Stakeholder risk | If environmental impacts from building works (e.g. dust, vibration and noise) are not considered, then there may be complaints received from the surrounding neighbourhood, resulting in potential reputational and stakeholder impacts. | Likely | Minor | Medium | 1. Reduce - Establish environmental control processes and procedures in place that are rolled out early in collaboration with the contractor. This should also include consideration to environmental controls required post operationalisation. Ensure this consideration has been taken on board in the stakeholder engagement plan and design considerations. 2. Reduce - Commission environmental studies throughout the course of the project to ensure the noise and vibration pollution can be controlled. | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Planning risk | If inadequate due diligence is performed during site selection relating to underlying utilities and ability to connect the site to surrounding utilities, there is a risk of scope creep due to additional works required to connect to surrounding utilities, leading to schedule delays and cost overruns. | Unlikely | Extreme | High | 1. Reduce - ensure a Site Selection and Acquisition Strategy is prepared, which includes robust due diligence through site investigations. | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Stakeholder risk | If local stakeholders, surrounding residents expectations of visual and acoustic and privacy impacts are not considered in planning and design, then landowners and stakeholders will feel unheard or unconsulted, resulting in reputational damage to the project. | Likely | Minor | Medium | 1. Reduce - Commission visual, acoustic and privacy surveys to identify options during design to ensure these impacts have been considered. | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Planning risk | If planning and preparation works do not effectively establish the previous use of the site e.g. mining, agriculture, then there is a risk that the site is contaminated, resulting in additional decontamination works, reputational damage, cost overruns and schedule delays. | Possible | Extreme | High | 1. Reduce - ensure a Site Selection and Acquisition Strategy is prepared, which includes robust due diligence through site investigations. | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Design inadequacy risk | If the asset design is different to the common design for that asset (e.g. trend of moving from single story school buildings to high rise schools in high density areas), there is a risk that asset management requirements have not been appropriately considered in project planning, leading to long term operations and maintenance cost increases and potential safety risks for school staff and students. | Possible | Major | High | 1. Reduce - As part of the project planning and design, engage with relevant SMEs to support asset management requirements throughout project delivery. | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Design inadequacy risk | If the project design does not consider appropriate transport connectivity (bus routes), kiss and drop facilities, car parking and accessibility requirements, then there there may be traffic impacts causing congestion once the school is operational, resulting in frustration and reputational damage to the project / State from the school users and local community. | Possible | Minor | Medium | 1. Reduce - Consider options for the school to develop detailed ‘Green Travel Plans’ for staff outlining all public and active transport opportunities and strategies by which to reduce private vehicle travel to the site. 2. Reduce - Ensure there are relevant stakeholders engaged in the design phase (e.g. urban planning, local community stakeholders, Education representatives etc.) | yes | yes | yes | yes
Social infrastructure | Education | School (Greenfield) | Planning risk | If there is ineffective planning of ingress and egress routes to support construction activity, then there is a risk of traffic impacts and congestion, and may also lead to additional enabling works, resulting in schedule and cost impacts. | Unlikely | Extreme | High | 1. Reduce - Commission a Preliminary Construction Management Report which details dedicated site access routes for truck drivers. This will also include requirements for dedicated traffic controllers at vehicle access points to direct traffic and uphold pedestrian safety. | yes | yes | yes | yes
Transport | Road | State road (Highway/Freeway) | Planning risk | If a dilapidation survey of existing public roads is not conducted with sufficient detail prior to commencement of construction, then there is a risk that road / asset decay during construction may be associated with the project’s construction, resulting in reputational damage, and cost overruns to support additional remedial works. | Likely | Moderate | High | 1. Reduce - Commission a detailed Dilapidation Survey prior to construction activity, and ensure this is reviewed and approved by site staff and relevant contractors to use as a source of truth of site conditions. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Construction workplace safety risk | If civilians / drivers are not aware of the rules in and around the worksite, then there is a risk of accidents involving civilians or construction workers, particularly when dealing with high volumes of traffic and vehicles travelling at high speed, and these may result in harm / workplace injuries / death. | Possible | Extreme | High | 1. Reduce - Engage the contractor to prepare project specific Health, Safety and Environment (HSE) Management Plans, with sufficient detail to cover scenarios related to the site. 2. Reduce - Ensure there is clear signage and appropriate traffic management personnel and procedures in place to manage safety risks. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Construction workplace safety risk | If construction planning does not consider operating around existing overhead power lines, there is a risk that power lines are disrupted, causing safety hazards for the site team, and schedule delays, cost overruns and reputational damage to the project. | Possible | Extreme | High | 1. Reduce - Consult with utilities partners to ensure utilities are not disrupted (e.g. power supply), with careful sequencing of works. 2. Reduce - Engage the contractor to prepare project specific Health, Safety and Environment (HSE) Management Plans, with sufficient detail to cover scenarios related to the site. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Stakeholder risk | If secondary impacts of construction activity (e.g. dust, noise, odour and visual intrusion) have not been planned for in stakeholder management plans, there is a risk that these impacts will create local opposition to the project, resulting in reputational damage, and may result in schedule delays and cost impact. | Likely | Minor | Medium | 1. Reduce - Establish environmental control processes and procedures in place that are rolled out early in collaboration with the contractor. This should also include consideration to environmental controls required post operationalisation. Ensure this consideration has been taken on board in the stakeholder engagement plan and design considerations. 2. Reduce - Commission environmental studies throughout the course of the project to ensure the noise and vibration pollution can be controlled. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Planning risk | If there are inaccuracies in historical record keeping, then there may be crossings or clashes with existing utilities (e.g.other pipes, voltage or optic fibre cables) resulting in schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - allow time for services searching and potholing beforehand and utilise non-destructive digging equipment and techniques. 2. Accept - allow cost and schedule contingency for the discovery, and relocation of utilities. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Weather risk | If there is inaccurate analysis on the weather conditions of the specific site, there is a risk of insufficient provisions within contracts relating to wet weather days, resulting in schedule delays and cost overruns. | Possible | Moderate | Medium | 1. Reduce - Complete analysis of the expected rainfall at the site location and consider provisions within contingencies to support more realistic wet weather allowances. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Population/demographics risks | If there is inaccurate demand modelling (e.g. expected population growth / future use of the highway / green travel requirements), there is a risk that the design is inadequate to support future use, resulting in reputational damage and higher operations and maintenance costs for remedial works. | Possible | Major | High | 1. Reduce - Establish a process to reassess patronage modelling and validate assumptions as the project progresses. This may also include completing sensitivity analysis over variations to the modelling to consider contingency planning. 2. Accept - Consider appropriate risk allowances in business case and benefits realisation plan based on the sensitivity analysis. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Planning risk | If there is insufficient analysis of land acquisition requirements as part of project planning, there is a risk that project designs may require revisions, additional compensation costs to land owners and delays with land acquisition, resulting in cost overruns and schedule delays. | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Benefits realisation risk | If there is insufficient consideration of how the new highway will integrate with existing periphery road infrastructure, there is a risk of misalignment of designs, resulting in reputational damage, cost overruns and schedule delays (driven by remedial works). | Possible | Major | High | 1. Reduce - Commission site surveys to complete analysis of peripheral road environment and existing infrastructure during early planning to ensure these aspects are considered in project design. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Stakeholder risk | If there is poor engagement with Indigenous and European communities, there is a risk that heritage sites are not fully understood and are adversely impacted during construction activities, leading to schedule delays and reputational damage to the project. | Possible | Major | High | 1. Reduce - establish a dialogue with local Indigenous communities,and develop a Cultural Heritage Management Agreement / Plan which details how cultural heritage impacts will be considered throughout project delivery. 2. Reduce - Engage a Heritage Consultant (Aboriginal and European Heritage), Ecologist and Town Planner as part of project initiation to ensure these impacts have been identified and considered. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Compliance/regulatory risk | If there is poor engagement with relevant planning, environment and statutory bodies early in the project, there is a risk of delays with required approvals required to commence construction activity, resulting in cost overruns and schedule delays. | Possible | Moderate | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies. 2. Transfer - Develop a matrix of all required approvals and consider allocating risk to relevant contractors to obtain approval. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Stakeholder risk | If there is poor planning and community engagement relating to expecting traffic detours, roadworks and reduced speed, there is a risk of motorist frustration during constructions, leading to reputational damage to the project. | Likely | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / community groups. | yes | yes |  | yes
Transport | Road | State road (Highway/Freeway) | Planning risk | If there is poor understanding / documentation of geotechnical conditions (or ground conditions), there is a risk that these differ from those originally anticipated during project planning, resulting in schedule delays with tunneling activities and cost overruns. | Likely | Extreme | Critical | 1. Reduce - Commissioning of geotechnical analysis in order to understand ground conditions to inform project planning. 2. Transfer - Negotiate with proponents to share / accept risks associated with GBR’s. 3. Accept - Consider appropriate risk allowances in the cost estimate. | yes | yes |  | yes
Transport | Rail | Stations (Revamp/Greenfield/Combined) | Planning risk | If potential future uses of the station (e.g. driverless rolling stock) / broader transport network requirements (e.g. integration with light rail or other transport modes) are not considered or planned for, there is a risk of misalignment with surrounding infrastructure, resulting in future operational and reputational impacts. | Possible | Extreme | High | 1. Reduce - Early in the project (e.g. during the business case phase), engage with operational and industry/asset SMEs to understand long term strategy for asset utilisation and broader network considerations. | yes | yes |  | yes
Transport | Rail | Stations (Revamp/Greenfield/Combined) | Governance risk | If there is poor management of the complex interfaces between work packages (e.g. station, tunnel, rail) or with other projects with concurrent timeframes (e.g. relocation of assets / utilities), there is a risk that each of the projects progress at various paces, resulting in key misalignment between work package and project commissioning milestones, leading to project schedule delays. | Likely | Major | High | 1. Reduce - Document all known dependencies across work packages and projects, and establish a cross work package / cross project dependency management forum in order to track and govern these dependencies through project delivery. 2. Reduce - Where possible, consider co-locating / sharing resources across projects / work packages to help identify and manage interfaces between the various projects / packages. | yes | yes |  | yes
Transport | Rail | Stations (Revamp/Greenfield/Combined) | Planning risk | If there is poor planning of periphery infrastructure, there is a risk of civilians trespassing into the rail corridors / throwing objects onto train / tracks from platform, resulting in additional operations and maintenance impacts, as well as civilian health / safety impacts. | Possible | Moderate | Medium | 1. Reduce - In planning / design, consider options such as platform screen doors which prevent passengers falling off platforms onto the tracks. They are also effective at reducing trespass into the rail corridor and the opportunity for passengers to throw objects onto trains or tracks from the platform. | yes | yes |  | yes
Transport | Rail | Stations (Revamp/Greenfield/Combined) | Public Safety risk | If there is poor planning or design of the station, there is a risk of crowded platforms and access / egress points, especially with stations located under ground level, resulting in civilian safety impacts (or congestion / delays to fast evacuation if necessary). | Rare | Extreme | Medium | 1. Reduce - Ensure potential operational impacts are well understood in the start of the project through stakeholder consultation. 2. Reduce - Ensure there are operational, asset and safety SMEs involved in the design phase, including requirements for sign off of project designs. 3. Reduce - Develop a plan for identification and management of operational risks and impacts during design. | yes | yes |  | yes
Transport | Rail | Stations (Revamp/Greenfield/Combined) | Planning risk | If there is poor understanding / documentation of geotechnical conditions (or underground conditions), there is a risk that these differ from those originally anticipated during project planning, resulting in delays with tunneling activities (for station development), leading to schedule delays and cost overruns. | Likely | Extreme | Critical | 1. Reduce - Commissioning of geotechnical analysis in order to understand ground conditions to inform project planning. 2. Transfer - Negotiate with proponents to share / accept risks associated with GBR’s. 3. Accept - Consider appropriate risk allowances in the cost estimate. | yes | yes |  | yes
Transport | Rail | Tunnel (Rail) | Planning risk | If potential future technologies or modelling of the use of the asset (e.g. driverless rolling stock population growth) / broader transport network requirements (e.g. integration with rail, battery based trains, driverless trains) are not considered or planned for, there is a risk of misalignment with surrounding infrastructure, resulting in future operational and reputational impacts. | Possible | Extreme | High | 1. Reduce - Early in the project (e.g. during the business case phase), engage with operational and industry/asset SMEs to understand long term strategy for asset utilisation and broader network considerations. | yes | yes |  | yes
Transport | Rail | Tunnel (Rail) | Planning risk | If there is inaccurate modelling of expected patronage demand growth on travel routes, there is a risk that more passengers use the public transport system more often or earlier than the model predicts, leading to unsustainable use of the transport system, and higher operations and maintenance costs to maintain / remediate routing and timetabling in the future. | Possible | Major | High | 1. Reduce - Establish a process to reassess patronage modelling and validate assumptions as the project progresses. This may also include completing sensitivity analysis over variations to the modelling to consider contingency planning. 2. Accept - Consider appropriate risk allowances in business case and benefits realisation plan based on the sensitivity analysis. | yes | yes |  | yes
Transport | Rail | Tunnel (Rail) | Planning risk | If there is insufficient analysis of land acquisition requirements as part of project planning, there is a risk that project designs may require revisions, additional compensation costs to land owners and delays with land acquisition, resulting in project cost overruns and schedule delays. | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. | yes | yes |  | yes
Transport | Rail | Tunnel (Rail) | Compliance/regulatory risk | If there is poor engagement with relevant planning, environment and statutory bodies early in the project, there is a risk of delays with required approvals required to commence construction activity, resulting in increased costs and schedule delays. | Possible | Moderate | Medium | 1. Reduce - ensure the stakeholder engagement plan captures engagement with relevant government agencies and that this activity takes place early on. 2. Reduce - project team or vendor team contains personnel who have experience with relevant state based requirements, and experience in liaising with the relevant departments. 3. Reduce - carry out the necessary Indigenous & European assessments and consultation investigations early in the project. 4. Transfer - Develop a matrix of all required approvals and consider allocating risk to relevant contractors to obtain approval. | yes | yes |  | yes
Transport | Rail | Tunnel (Rail) | Planning risk | If there is poor understanding / documentation of geotechnical conditions (or underground conditions), there is a risk that these differ from those originally anticipated during project planning, resulting in schedule delays with tunneling activities and cost overruns. | Likely | Extreme | Critical | 1. Reduce - Commissioning of geotechnical analysis in order to understand ground conditions to inform project planning. 2. Transfer - Negotiate with proponents to share / accept risks associated with GBR’s. 3. Accept - Consider appropriate risk allowances in the cost estimate. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Skilled labour supply risk | If there are a heightened number of infrastructure (or transport specific) projects in the pipeline, there is a risk of insufficient skilled resources being available in the market to adequately support the project, resulting in sub-optimal resourcing, lower quality project outcomes or cost overruns (if paying premium costs for key resources). | Likely | Major | High | 1. Reduce - During project planning, establish a resource management plan which identifies the key resources required throughout delivery, and develop strategies to recruit and retain key resources. This includes potential options to pay premium costs or agreeing long term contracts for resources with key skills. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Schedule risk | If there are extended lockdowns and border closures as a result of COVID-19 coupled with poor planning and sequencing of procurement activity, there is a risk of delays with the arrival of plant, raw materials and equipment required to progress the project due to global supply and shipping issues, leading to schedule delays. | Possible | Major | High | 1. Transfer - Negotiate a preferred procurement model to transfer risk allocations to relevant proponents. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Quality risk | If there are ineffective quality control / quality assurance procedures in place, there is a risk of defects from earlier design/construction of viaduct structure becoming apparent during the maintenance term, leading to higher operations and maintenance costs. | Likely | Major | High | 1. Reduce - establish and agree a Quality Management Plan with the contractor which includes various quality assurance and quality control processes. This should involve inspections, hold and witness points and other site surveillance activity, with clear acceptance criteria which is signed off by relevant operational staff. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Construction risk (engineering and build) | If there is an unexpected failure or damage to TBM (Tunnel Boring Machine) as part of tunneling activity, there is a risk that a second TBM may require procurement and mobilisation, resulting in schedule delays and cost overruns. | Possible | Major | High | 1. Transfer - Agree with contractors to own risk allocation in the scenario of TBM failure or damage. 2. Reduce - consider contingency plans to procure a secondary TBM to support. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Benefits realisation risk | If there is inaccurate modelling of expected traffic levels on routes, there is a risk that traffic levels are higher than anticipated (leading to higher operations and maintenance costs), or conversely, there is a risk of toll revenues not being adequate to maintain a the project's BCR, resulting in inefficient use of project funds and unrealised project benefits. | Possible | Moderate | Medium | 1. Reduce - Establish a process to reassess traffic modelling and validate assumptions as the project progresses. This may also include completing sensitivity analysis over variations to the modelling to consider contingency planning. 2. Accept - Consider appropriate risk allowances in business case and benefits realisation plan based on the sensitivity analysis. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Project management risk | If there is ineffective management of contractors and their delivery of work, there is a risk of contractor claims, leading to schedule delays and cost overruns. | Likely | Moderate | High | 1. Reduce - establish a Vendor & Contract Management Plan which clearly defines contractor deliverables, KPIs and reporting requirements. 2. Integrate contractor payment milestones to quality criteria defined within the quality management plan to ensure the the Owner has appropriate powers to withhold payments for sub-par quality deliverables. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Planning risk | If there is insufficient analysis of land acquisition requirements as part of project planning, there is a risk that project designs may require revisions, additional compensation costs to land owners and delays with land acquisition, resulting in cost overruns and schedule delays. | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Stakeholder risk | If there is insufficient or ineffective engagement with community and key stakeholders, there is a risk of community / stakeholder opposition to the project, its scope or preferred construction options, resulting in a need for additional stakeholder engagement / communications and schedule delays. | Likely | Moderate | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Planning risk | If there is poor analysis relating to expected road noise and potential vehicle mix, there is a risk that once the tunnel is operational, the road noise is above regulatory limits, resulting in additional operations and maintenance costs to rectify. | Possible | Major | High | 1. Reduce - Establish environmental control processes and procedures in place that are rolled out early in collaboration with the contractor. This should also include consideration to environmental controls required post operationalisation. Ensure this consideration has been taken on board in the stakeholder engagement plan and design considerations. 2. Reduce - Commission environmental studies throughout the course of the project to ensure the noise and vibration pollution can be controlled. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Stakeholder risk | If there is poor engagement with Indigenous communities, there is a risk that heritage sites are not fully understood and are adversely impacted during construction activities, leading to schedule delays and reputational damage to the project. | Possible | Major | High | 1. Reduce - establish a dialogue with local Indigenous communities,and develop a Cultural Heritage Management Agreement / Plan which details how cultural heritage impacts will be considered throughout project delivery. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Compliance/regulatory risk | If there is poor engagement with relevant planning, environment and statutory bodies early in the project, there is a risk of delays with required approvals required to commence construction activity, resulting in cost overruns and schedule delays. | Possible | Moderate | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies. 2. Transfer - Develop a matrix of all required approvals and consider allocating risk to relevant contractors to obtain approval. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Governance risk | If there is poor management of the complex interfaces between work packages (or with other projects with concurrent time frames - e.g. relocation of assets / utilities), there is a risk that each of the projects progress at various paces, resulting in key misalignment between work package and project commissioning milestones, leading to schedule delays. | Likely | Major | High | 1. Reduce - Document all known dependencies across work packages and projects, and establish a cross work package / cross project dependency management forum in order to track and govern these dependencies through project delivery. 2. Reduce - Where possible, consider co-locating / sharing resources across projects / work packages to help identify and manage interfaces between the various projects / packages. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Stakeholder risk | If there is poor planning and community engagement relating to expecting traffic detours, roadworks and reduced speed, there is a risk of motorist frustration during constructions, leading to reputational damage to the project. | Likely | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / community groups. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Planning risk | If there is poor planning relating to complementary / enabling works / site access required to achieve project outcomes, there is a risk of project scope changes, resulting in additional scope and cost overruns. | Possible | Moderate | Medium | 1. Reduce - ensure a Site Selection and Acquisition Strategy is prepared, which includes robust due diligence through site investigations. | yes | yes |  | yes
Transport | Road | Tunnel (Road) | Planning risk | If there is poor understanding / documentation of geotechnical conditions (or underground conditions), there is a risk that these differ from those originally anticipated during project planning, resulting in delays with tunneling activities, leading to schedule delays and cost overruns. | Likely | Extreme | Critical | 1. Reduce - Commissioning of geotechnical analysis in order to understand ground conditions to inform project planning. 2. Transfer - Negotiate with proponents to share / accept risks associated with GBR’s. 3. Accept - Consider appropriate risk allowances in the cost estimate. | yes | yes |  | yes
Energy | Photovoltaics | Utility solar/solar farm | Planning risk | If relevant state planning bodies, the network provider (for augmentation requirements) and community groups (for visual impacts) are not consulted early on, then there may be issues with obtaining the planning, environmental and statutory approvals required for construction resulting in schedule and cost impacts. | Likely | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with the network provider, relevant local / state planning bodies and relevant community groups. 2. Reduce - project team or vendor team contains personnel who have experience with relevant state based requirements, and experience in liaising with the relevant departments. 3. Accept - the developer may need to pay for network augmentation (for either transmission or distribution). | yes | yes | yes | yes
Energy | Photovoltaics | Utility solar/solar farm | Stakeholder risk | If early engagement of stakeholders (impacted by site works) does not take place, then they may refuse access to their property when required, or make complaints resulting in reputational and schedule impacts. | Possible | Moderate | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local businesses and community stakeholders. 2. Reduce – Consider strategies to engage with relevant stakeholders to support site access needs (e.g. cost reimbursement models, community forums etc.). | yes | yes | yes | yes
Energy | Photovoltaics | Utility solar/solar farm | Planning risk | If weather conditions (i.e. wet seasons) are not considered in project planning / operational use, then weather disruptions may occur during the construction phase (or in operations) resulting in schedule and cost impacts, and limitations in being able to achieve benefits. | Unlikely | Major | Medium | 1. Reduce - early schedule planning ensures construction takes place over the dry season, with the early decision made on contingency options if project progress is impacted by weather conditions. The schedule should also have appropriate provisions to accommodate seasonality. | yes | yes | yes | yes
Energy | Photovoltaics | Utility solar/solar farm | Currency risk | If hedging does not take place, then movements in foreign exchange rates may lead to cost impacts - i.e., increase in costs for key components (e.g. solar panels) | Possible | Moderate | Medium | 1. Accept - Ensure there is budget contingency to remediate any FOREX issues (or consider allowances within existing budget). 2. Reduce - Engage with FOREX experts to understand if hedging on required currencies can be executed. | yes | yes | yes | yes
Energy | Photovoltaics | Utility solar/solar farm | Supply chain risk | If there are shipping difficulties and disruption of global supply chains, then this may cause solar specific materials/equipment (which are higher complexity / specialty equipment) to not be available, resulting in schedule and cost impacts. | Likely | Major | High | 1. Accept - Include cost and schedule contingency for supply chain impacts. 2. Reduce – Complete supply chain planning across key procurement categories, and consider strategies to pre-purchase, local storage, local supply chain market development etc. | yes | yes | yes | yes
Energy | Photovoltaics | Utility solar/solar farm | Operational risk | If there are delays in connecting the solar farm to the grid, then there can be a detrimental impact to the contractor (dependant on contract type) and lengthened commissioning timelines resulting in cost and schedule impacts. | Likely | Major | High | 1. Reduce - ensure that the structured stakeholder management plan includes strong engagement with the relevant state based agency as well as with the Network Service Provider. 2. Reduce - consider risk sharing known solar farm construction risks (i.e. connection delays) to encourage bidding. | yes | yes | yes | yes
Energy | Photovoltaics | Utility solar/solar farm | Planning risk | If appropriate risk sharing does not take place with the proponent in relation to prevalent solar risks (e.g. connection delays), then there may be limited appetite from construction contractors to bid for work, resulting in cost and schedule impacts. | Likely | Major | High | 1. Reduce – Increase transparency with proponents related to risk allocation, particularly relating to connections, approvals and requirements on specific solar farm construction risks (i.e. connection delays). | yes | yes | yes | yes
Waste | Waste | Waste processing facility | Weather risk | If consideration of flooding risks does not take place in the design phase, then there is a risk of damage to the WWTP facility in the event of flooding resulting in operating impacts. | Possible | Major | High | 1. Reduce - Ensure climate change considerations take place early in the planning process when site acquisition decisions are being made (i.e. decision between flooding risk and access to discharge site). | yes | yes |  | yes
Waste | Waste | Waste processing facility | Construction workplace safety risk | If construction safety procedures aren’t clearly defined (given WWTPs have confined spaces, deep water, biological hazards and explosion risks) then there can be safety incidents on site resulting in compliance, safety and cost risks. | Unlikely | Major | Medium | 1. Reduce - ensure the contractor has been trained on the safety procedures for the facility prior construction works commencement. 2. Transfer - ensure the contractor’s safety management system adopts the requirements for the site in question and has a robust permit to work system detailed and adhered to. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Financial/cost/budget risk | If contamination investigations are not properly carried out then construction work may uncover the presence of contaminants resulting in schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - perform contamination investigations early on, and plan for contamination disposal, and remediation, with these activities included in schedule & cost contingencies. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Stakeholder risk | If early engagement of stakeholders (closely situated to the site) does not take place, then they may refuse access to their property if / when required, or make complaints resulting in cost and schedule impacts. | Possible | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local businesses and community stakeholders. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Stakeholder risk | If early engagement with impacted stakeholders does not take place, then there may be delays encountered in land acquisition resulting in schedule and cost impacts | Possible | Major | High | 1. Reduce - plan for site assessment and acquisition very early on in the project. Ensure there is strong engagement with impacted stakeholders. Stakeholder appetite for a sale will have to be assessed, contingency allowed for and an alternative site may be needed. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Compliance/regulatory risk | If early engagement with the relevant state based environmental protection agency (EPA) does not take place, then the plant may be in breach of requirements resulting in potential operational and cost impacts (i.e. fines and remediation costs). | Possible | Major | High | 1. Reduce - consult with the EPA early on to understand current and any potential future compliance requirements. Ensure that these compliance requirements have been factored into the site’s design and operations. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Planning risk | If existing infrastructure is in poor condition, then there can be asset failure (e.g. structural failures or pipe failures / bursts) whilst works are occurring resulting in compliance, health and safety, operational, cost and schedule impacts. | Likely | Major | High | 1. Reduce - ensure consultation and conditions assessments take place with the operations team to understand the state of existing infrastructure. Once identified, ensure sequencing of works takes place so that riskier parts are replaced first. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Planning risk | If existing infrastructure is not suitable for immediate work (e.g. pipes or tanks have not been adequately flushed prior to cut-ins occuring), then it will have to be cleaned, resulting in schedule and cost overruns. | Possible | Moderate | Medium | 1. Reduce - consult with the operations team early on to understand the suitability of existing infrastructure and pre work required for cut-ins / tie-ins. 2. Accept - Include sufficient schedule contingency for facility preparation. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Environmental risk | If odour or midge control precautions are not in place, then odours may be emitted from site, or significant midge activity will take place, resulting in stakeholder complaints and enforcement notices. | Possible | Moderate | Medium | 1. Reduce - ensure odour control and midge control procedures are in place (e.g. installation of odour control units, or chemical dosing). | yes | yes |  | yes
Waste | Waste | Waste processing facility | Population/demographics risks | If population growth and it’s timing for the area where the WWTP is to be situated in is not adequately accounted for, then the plant may either fail at being able to process increased volumes in the future due to expansion constraints or have built in too much capacity too quickly resulting in operational (i.e. inefficient to operate) and compliance impacts (e.g. failing to meet environmental discharge standards). | Possible | Moderate | Medium | 1. Reduce - Provision modelling work to provide guidance on potential population growth rates etc. for the area and associated plant capacity staging built into planning and design. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Stakeholder risk | If relevant state planning bodies and community groups are not consulted early on, then there may be issues with obtaining the planning, environmental and statutory approvals required for construction and operation resulting in schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / state planning bodies and relevant community groups. 2. Reduce - project team or vendor team contains personnel who have experience with relevant state based requirements, and experience in liaising with the relevant departments. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Skilled labour supply risk | If resources / contractors with experience in waste facility construction are not involved early in the project, or not available to be involved, then there may be issues encountered during the delivery of the project resulting in cost, schedule and quality impacts. | Likely | Major | High | 1. Reduce - Extend procurement to overseas for organisations who have experience in the construction / delivery of waste processing projects. 2. Reduce - Ensure delivery partner has experience in waste facility construction projects and include this as a requirement in the tendering process. 3. Reduce - During project planning, establish a resource management plan which identifies the key resources required throughout delivery, and develop strategies to recruit and retain key resources. This includes potential options to pay premium costs or agreeing long term contracts for resources with key skills. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Operational risk | If service continuity planning (e.g. diversions to other WWTPs or pumping to storage tanks / lagoons) does not take place for a WWTP in an area that still needs to be serviced, then operations will be impacted resulting in compliance, stakeholder and operations risk. | Possible | Moderate | Medium | 1. Reduce - Perform service continuity planning with operations staff and asset managers to understand whether diversions can take place and for how long. Communicate construction windows (with contingencies) so that operations at other sites are aware. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Environmental implications risk | If site investigations are not comprehensive enough, then hard rock or other challenging ground conditions etc. may be encountered requiring a change in construction approach and resulting in cost and schedule impacts. | Possible | Moderate | Medium | 1. Reduce - ensure comprehensive site inspections and a geotechnical study takes place early in the design phase at the latest. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Stakeholder risk | If sufficient analysis does not take place over the impact of construction to nearby landowners and business then the compensation amounts required during delivery may increase resulting in cost impacts. | Possible | Major | High | 1. Reduce - Identify the exact locations and number of impacted landowners and businesses early on and budget for the different types of impacts during construction (e.g. needing to compensate businesses for loss of business) and compensation amounts required against each. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Stakeholder risk | If sufficient stakeholder engagement and consultation does not take place, then there may be local opposition to the facility resulting in reputational impacts. | Possible | Major | High | 1. Reduce - ensure results of environmental studies are and benefits of the facility are communicated to all impacted stakeholders. Ensure key operational impacts (noise, odour and visual impacts) are mitigated in design and communicated to stakeholders impacted and the wider community. | yes | yes |  | yes
Waste | Waste | Waste processing facility | Planning risk | If the condition of the existing asset isn’t well understood, then there may be further deterioration (e.g. poor quality concrete structures with rusted rebar and crumbling concrete or corroded pipes) uncovered during tie-ins requiring the order of new parts and further work resulting in cost and schedule impacts. | Possible | Moderate | Medium | 1. Reduce - Perform detailed conditions assessment with the operations team during the design phase. 2. Accept - include cost and schedule contingency for parts deterioration (i.e. ordering new parts and labour time for installation). | yes | yes |  | yes
Waste | Waste | Waste processing facility | Planning risk | If the layout of the existing site isn’t well understood, then there may be design errors requiring further work (i.e. interfaces with existing equipment) or unforeseen pipe clashes / intersections resulting in cost and schedule impacts. | Likely | Major | High | 1. Reduce - Ensure operations team is made available to the planning & design contractor with sufficient time allowed for site inspections. 1. Reduce - Ensure that the contractor is tasked with modelling (i.e. on CAD) out interfaces as well. 2. Transfer - Transfer risk of design errors back to the contractor (i.e. they will be back charged for impacts resulting from design errors). | yes | yes |  | yes
Waste | Waste | Waste processing facility | Stakeholder risk | If there is poor planning and community engagement relating to the proposed waste processing facility, there is a risk of community frustration and dissatisfaction, leading to reputational damage to the project, and schedule delays. | Likely | Major | High | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local / community groups. | yes | yes |  | yes
Water | Water | Water service pipes | Stakeholder risk | If early engagement of stakeholders (impacted by site works) does not take place, then they may refuse access to their property when required, or make complaints resulting in stakeholder and schedule impacts. | Possible | Moderate | Medium | 1. Reduce - Develop a structured stakeholder management plan, which includes early engagement with relevant local businesses and community stakeholders. | yes | yes | yes | yes
Water | Water | Water service pipes | Compliance/regulatory risk | If relevant state based requirements are not well understood early on, then there may be delays in obtaining access to land (e.g. road and rail crossings) leading to schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - ensure the stakeholder engagement plan captures engagement with relevant government agencies and that this activity takes place early on. 2. Reduce - project team or vendor team contains personnel who have experience with relevant state based requirements, and experience in liaising with the relevant departments. | yes | yes | yes | yes
Water | Water | Water service pipes | Design inadequacy risk | If there are further changes to design required, then there may be an increase in material quantity required resulting in cost impacts. | Likely | Moderate | High | 1. Reduce - carefully review estimates / takeoffs during the detailed design review process. 2. Reduce - involve operations in the design review process. | yes | yes | yes | yes
Water | Water | Water service pipes | Planning risk | If there are inaccuracies in historical record keeping, then there may be crossings or clashes with existing utilities (e.g.other pipes, voltage or optic fibre cables) resulting in schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - allow time for services searching and potholing beforehand and utilise non-destructive digging equipment and techniques. 2. Accept - allow cost and schedule contingency for the discovery, and relocation, of utilities. | yes | yes | yes | yes
Water | Water | Water service pipes | Construction risk (engineering and build) | If there are large rocks (or other ground conditions) encountered, then there may be a need to change the construction approach (e.g. including rock excavation) which will result in cost and schedule impacts. | Likely | Moderate | High | 1. Reduce - ensure comprehensive site inspections and a geotechnical study takes place early in the design phase at the latest. | yes | yes | yes | yes
Water | Water | Water service pipes | Environmental implications risk | If there are water tables / springs located along the pipeline’s route then there may be additional pumping work and groundwater diversion works required resulting in schedule and cost impacts. | Possible | Moderate | Medium | 1. Accept - allow schedule & cost contingency for any additional pumping and groundwater diversion work required. | yes | yes | yes | yes
Water | Water | Water service pipes | Project management risk | If vendor quality obligations are not well communicated and contractually enforced, then integrity issues may emerge during pressure testing resulting in potential cost, schedule and quality impacts. | Unlikely | Major | Medium | 1. Reduce - ensure vendors have strong quality obligations Reduce - ensure there is schedule contingency to remediate any integrity issues. | yes | yes | yes | yes
Water | Water | Water service pipes | Planning risk | If weather conditions (i.e. dry seasons) are not considered in planning, then weather disruptions may occur during the construction phase resulting in schedule and cost impacts. | Unlikely | Major | Medium | 1. Reduce - early schedule planning ensures construction takes place over the dry season, with the early decision made as to whether two dry seasons are required and an attempt made to expedite kilometres covered within the dry season. | yes | yes | yes | yes
Water | Water | Water pipelines (Greenfield/Brownfield) | Schedule risk | If construction takes longer than expected and timelines agreed with customers to facilitate tie-ins are too short, then there can be delays in resuming services resulting in contract breaches and reputational impacts. | Possible | Moderate | Medium | 1. Accept - Engage with customers early on to understand how long supply can be cut off for and negotiate timelines with enough contingency given the complexity associated with brownfield work. | yes | yes | yes | yes
Water | Water | Water pipelines (Greenfield/Brownfield) | Supply chain risk | If materials handling during transport and storage is not adequate, then there is a risk that materials are either damaged during transit or onsite resulting in quality, cost and schedule impacts. | Likely | Minor | Medium | 1. Reduce - ensure there is sufficient schedule contingency (e.g. shipments of materials such pipes should commence before construction starts, with a key materials onsite for start of construction). Through this, identification of defects can take place early on, allow additional ordering of spare parts in advance and ensure that storage areas (e.g. pipe yards) are ready as contingency. 2. Reduce - ensure there is a structured and resource based inspection test plan which involves inspection of materials upon arrival on site. 3. Reduce - ensure there is appropriate asset storage with a robust materials handling processes in place. | yes | yes | yes | yes
Water | Water | Water pipelines (Greenfield/Brownfield) | Planning risk | If potential future transmission capacity requirements are not adequately captured and considered in design, then future commercial opportunities will be missed due to pipeline constraints resulting in financial impacts. | Unlikely | Major | Medium | 1. Reduce - consult early on with the business development / commercial team to understand potential future commercial opportunities. Ensure that these requirements are agreed broadly and reflected in requirements and designs. | yes | yes | yes | yes
Water | Water | Water pipelines (Greenfield/Brownfield) | Compliance/regulatory risk | If relevant state based land access requirements are not well understood early on, then there may be delays in obtaining access to land (e.g. ROW, road and rail crossings, private lands, utilities) leading to schedule and cost impacts. | Possible | Moderate | Medium | 1. Reduce - ensure the stakeholder engagement plan captures required engagement with relevant government agencies and that this activity takes place early on. 2. Reduce - project team or vendor team contains personnel who have experience with relevant state based requirements, and experience in liaising with the relevant departments or agencies. | yes | yes | yes | yes
Water | Water | Water pipelines (Greenfield/Brownfield) | Stakeholder risk | If stakeholder opposition to the project is not understood early on, then there may be opposition encountered whilst trying to obtain approvals for gas pipeline infrastructure resulting in cost and schedule impacts. | Possible | Minor | Medium | 1. Reduce - ensure that a stakeholder engagement plan has been produced and captures relevant protest groups or individuals with plans in place to engage with them. | yes | yes | yes | yes
Water | Water | Water pipelines (Greenfield/Brownfield) | Operational risk | If the asset operations team is not sufficiently involved during planning, design and construction, then there may be operations and maintenance issues post handover resulting in operational, reputation and financial risks. | Possible | Moderate | Medium | 1. Reduce - ensure the operations team has a an active role on the project team / governance committee, with appropriate input into planning, design, oversight across key phases, and input into the practical completion decision. 2. Reduce - ensure operations planning is completed early on, there is a structured checklist to tracking operational readiness. | yes | yes | yes | yes
Water | Water | Water pipelines (Greenfield/Brownfield) | Project management risk | If vendor quality obligations are not well communicated and contractually enforced, then integrity issues (e.g. pipeline leak / rupture or loss of containment) may emerge during hydrotesting resulting in potential cost, schedule and quality impacts. | Unlikely | Major | Medium | 1. Reduce - ensure strong quality obligations are in place for vendors and contractors and are enforced (aligned to Australian Standards at a minimum). 2. Reduce – ensure a fit for purpose Quality Management Plan is in place, which includes activities such as pipeline testing, QA/QC, hydro tests, leak detection systems etc. 3. Reduce - ensure there is schedule and cost contingency to remediate any integrity issues. | yes | yes | yes | yes
Water | Water | Water pipelines (Greenfield/Brownfield) | Planning risk | If weather conditions (i.e. wet seasons) are not considered in project planning / operational use, then weather disruptions may occur during the construction phase (or in operations) resulting in schedule and cost impacts, and limitations in being able to achieve benefits. | Unlikely | Major | Medium | 1. Reduce - early schedule planning ensures construction takes place over the dry season, with the early decision made on contingency options if project progress is impacted by weather conditions. The schedule should also have appropriate provisions to accommodate seasonality. | yes | yes | yes | yes

## Sector risks
Sector | Risk description | Rating | Trend
Transport | Increasing prevalence of social license issues as network disruption from multiple concurrent projects heightens impacts in urban areas. | High | Increasing
Transport | Greater attention required to cost and scope environmental and land contamination, which may result in costs and delays. | High | Increasing
Transport | Increasing prevalence of tunneling in projects will require greater specialist capability nationally, to manage increasing risks on ground movements as well as geotechnical issues. | Critical | Increasing
Transport | Land acquisition challenges will result in increased project costs due to underestimated compensation costs to landowners, and/or late changes affecting project scope and design | Critical | Increasing
Transport | Project based rather than network approach, resulting in re-work and benefits underachievement. | High | Increasing
Energy | Complex projects like hydroelectric dams are at risk of cost overrun. | High | Increasing
Energy | Underlying connection and transmission infrastructure to support renewable energy is underdeveloped, creating potential for low grid resilience and ‘orphan infrastructure’ unable to connect into the network. | Critical | Increasing
Energy | Lack of policy coordination is disbursing investment focus, leading to lower investment effectiveness and less efficient investment parameters. | Critical | Increasing
Energy | Consumer preference is changing type of energy demanded, with consumers preferring energy produced through renewables. | Medium | Increasing
Water | Complex governance issues with dispersed authority creates decision uncertainty for delivering the infrastructure pipeline. | High | Increasing
Water | Inability to access skilled migrants increases competition for talent, with cost of labour expected to rise while the quality of labour reducing. | High | Increasing
Water | Lack of national policy framework creates uncertainty for investment. | Critical | Increasing
Social Infrastructure | Business cases for social infrastructure are frequently without adequate O&M funding resulting in significant un-scoped financial burden for governments. | Critical | Increasing
Social Infrastructure | Business case guidelines favour economic infrastructure projects compared to social projects. | High | Increasing
Social Infrastructure | Demand shifts and population growth may result in school infrastructure becoming redundant well within the asset life. | Medium | Increasing
Social Infrastructure | Over-reliance on health professionals rather than care models is resulting in infrastructure not meeting needs. | High | Increasing
Waste | Inadequate infrastructure development coordination for all stages of the waste cycle, from collection to aggregation to treatment, will cause cost overruns and benefits underruns. | Critical | Increasing
Waste | Ineffective community engagement continues to lead to social license problems causing project delays and increased costs. | Critical | Increasing
Waste | Security and scale of supply of feed stocks for waste to energy projects. | Medium | Decreasing
Waste | Low levels of market and regulatory readiness. | High | Increasing
Telecommunications and digital | Underinvestment in network improvements. | High | Increasing
Telecommunications and digital | Lack of market incentives for regional and remote access. | High | Increasing
Telecommunications and digital | Declining returns on private investment and ‘free rider’ issues for 5G investment | Medium | Decreasing
Telecommunications and digital | Poor understanding of existing utility infrastructure, leading to scope growth and cost overruns. | Critical | Increasing